## Sheet1
Date Entered | Site | Reviewer | Action Item | Syneos Response (include date and initials) | AbbVie Response (include date and initials) | Status of AI (to be completed by AbbVie) | LINK TO TMF | Additional LINKS | Additional LINKS | Region | Country | Date FU Action Updated | Syneos FU Action | Count of missing documents
2025-01-16 | 104 | Caroline | Missing onsite IP temp logs | 16Ap NE: 8-9Oct2023 TE Form Global Version ID 30570_551735_550591 14Apr25LS: ongoing FU with the site. Expect to be completed by the deadline. 14Apr NE: site was reminded to provide the forms or explanations. 24MAR25 ADM: excursion noted for a time period exceeding 6 hours were noted for:22APR22,06MAY22, 19MAY22,25-27May22,5JUN22,7-13JUN22,15-17JUN22,20-27JUN22, 29-31AUG22,21-22AUG23, 8-9OCT23, 2NOV23. TE forms requested to the site. 18MAR25 ADM: Apr and May 2024 on file at INBOX-452458-59 14Mar NE: CTM to check TE and contact the site if necessary. 30Jan2025 JC: Temp logs have been uploaded to TMF (INBOX-436713, INBOX-436714, INBOX-436715, INBOX-436716, INBOX-436717, INBOX-436718, INBOX-436719, INBOX-436720). 17Jan2025 JC: Followed up with CRA. | 16JAN2025 SP - we have 2 temp logs filed: VV# 341956 (NTF, not actual temp log) & 341958 (this covers 13AUG23 to 19AUG2023). No other temp logs posted in TMF 29JAN2025 SP - still missing 04Feb2025 MS - INBOX-436718 Log from 11-Sep-22 to 19-Nov-22 uploaded on 31-Jan-25 (INCOMPLETE Status). Still missing 17-Feb-25 MS - 12 logs uploaded - see VV#s and periods covered - Ready for AbbVie review 05March2025 CR: Possible TE>25oC with no TE form filed :20Apr, 22Apr2022 , 06, 09, 10, 11, 12, 16, 18, 19, 20, 23, 24, 25,26, 27, 28, 29 May2022 VV-TMF-496711. 02Jun2022, 11 Jun daily to 28Jun2022 VV-TMF-496706. 07,11,27, Jul 2022 25,28,29,30, 31 Aug 2022, VV-TMF-496718. 21,22Aug2023, 08. 09Oct2023, 02Nov2023 VV-TMF-496720. Apr2024 and May 2024 temp logs not filed. 19March20025 CR: logs not yet visible in VV. Will raise TEs to DM for review with clinical supplies. (IP logs_internal review) 21-Mar-2025 RP: April and May 2024 IP temp logs on file (VV-TMF-513691, VV-TMF-513688). Syneos please provide information on the Possible TEs. 25-Mar-25 RP: Syneos, please provide the VV#s to these TE forms when avaiable. Thanks. 26March2025 CR: Dm will include possible TEs noted in email to syneos today. | Re-opened | V-TMF-497008 06-Aug to 26-Aug-2024 VV-TMF-497011 01-Jul to 05-Aug -2024 VV-TMF-497010 01-Jun to 30-Jun -2024 VV-TMF-497007 01-Jan to 31-Mar-2024 VV-TMF-496720 12-Jun-2023 to 18-Jan-2024 VV-TMF-496714 25-Jan to 12-Jun-2023 VV-TMF-496716 16-Nov-2022 to 17-Feb-2023 VV-TMF-497014 11-Sep to 19-Nov-2022 VV-TMF-496718 01-Jul to 12-Sep-2022 VV-TMF-496706 02-Jun to 19-Jul-2022 VV-TMF-496711 26-Jan to 02-Jun-2022 VV-TMF-496710 09-Feb 2021 to 16-Feb-2022 VV-TMF-513691 May 2024 VV-TMF-513688 April 2024 |  |  | NAMER | USA | 2025-04-03 | Open